## about
ABOUT THIS PLANNING RESOURCE
Use this planning workbook to visualize and track your Frontline Enablment and Empowerment project. To start, add your company name, review the actions and milestones, add projected completion and start dates and assign activities to the memeber of your core project team. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.
This planning workbook helps you execute your journey to valuable Teams solutions for your frontline workers.

## plan ¦ ENABLE + EMPOWER
ENABLE + EMPOWER FRONTLINE WORKERS
Company name | [6 empty] | Legend: |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-09-16 | [7 empty] | June | [6 empty] | July | [34 empty] | August
Scrolling Increment: | 283 | time axis 2022-06-26 to 2022-08-20
Milestone description | Relevant resources | Category | Who needs to be consulted and informed? | Who does the work? | Assigned to | Progress | Start | Days | [56 empty] | S | time axis 2022-06-26 to 2022-08-20
START
Readiness to engage and execute next stages |  | Goal |  |  | List from people tab table | 0% |  | 6
Align on motivation for frontline worker enablement with Microsoft Teams |  | On Track |  |  |  | 0% |  | 2
Identify potential blockers to the project (i.e. complexities, risks) |  | On Track |  |  |  | 0% |  | 1
Identify core stakeholders– business, IT, and frontline decision makers |  | On Track |  |  |  | 0% |  | 1
Understand other in-progress initiatives related to frontline workers and impact |  | On Track |  |  |  | 0% |  | 1
Understand and socialize among your core project team the best practices and approach to building truly valuable solutions for frontline workers in Teams |  | On Track |  |  |  | 0% |  | 1
DISCOVER
Consensus on “What’s needed by whom and why?“ to get alignment on what would be of value to the frontline workers |  | Goal
Scope Discovery activities |  | On Track |  |  |  | 0% |  | 14
Define what’s needed and why through persona, problem, and user story |  | On Track |  |  |  | 0% |  | 8
Create and prioritize user stories that describe a potential solution |  | On Track |  |  |  | 0% |  | 4
Agreement on what’s needed and why by the frontline workforce |  | Milestone |  |  |  | 0%
Understand current workarounds and gaps |  | On Track |  |  |  | 0% |  | 2
Clear, confirmed “What’s in it for me?” for every persona the solution will serve |  | Milestone |  |  |  | 0%
Secured executive sponsorship |  | Milestone |  |  |  | 0%
Decision: Enable Frontline Workers with SMS Sign-in |  | Milestone |  |  |  | 0%
Decision: Shift-based access for Frontline Workers in Teams |  | Milestone |  |  |  | 0%
Decision: Delegate user management to FLMs through MyStaff portal |  | Milestone |  |  |  | 0%
ENVISION
Identify best solution leveraging FLW building blocks |  | Goal |  |  |  | 0% |  | 10
Map apps and capabilities that light up key scenarios and user stories |  | On Track |  |  |  | 0% |  | 2
Evaluate solution and sizing with architecture and building blocks defined |  | On Track |  |  |  | 0% |  | 2
Identify license needs based on confirmed scenarios and user stories |  | On Track |  |  |  | 0% |  | 2
Ensure devices and peripherals support the scenarios and user stories |  | On Track |  |  |  | 0% |  | 2
Decision: how FLWs will access Teams app – will they install it themselves or will app be pushed on their device. |  | Milestone |  |  |  | 0%
Decision: how FLWs will log in to Teams and manage their identity going forward |  | Milestone |  |  |  | 0%
Decision: device, application, and data security – approach to bring-you-own, corporate shared, and assigned device |  | Milestone |  |  |  | 0%
Identify relevant roles and responsibilities for execution |  | On Track |  |  |  | 0% |  | 2
Documented plan for technical enablement |  | Milestone |  |  |  | 0%
Documented plan for adoption |  | Milestone |  |  |  | 0%
Documented plan for pilot execution |  | Milestone |  |  |  | 0%
BUILD
Build solution prototype and validate through a pilot |  | Goal |  |  |  | 0%
1P ¦ Walkie Talkie |  | On Track |  |  |  | 0%
1P ¦ Praise |  | On Track |  |  |  | 0%
1P ¦ Tasks (Core & Publishing) |  | On Track |  |  |  | 0%
1P ¦ Shifts implementation |  | On Track |  |  |  | 0%
Define Teams settings |  | On Track |  |  |  | 0%
Prevent unintentional sharing of sensitive items |  | On Track |  |  |  | 0%
Limit when and where FLWs can access Teams on a shared device |  | On Track |  |  |  | 0%
Restrict which applications FLWs on my shared devices can use in Teams itself |  | On Track |  |  |  | 0%
Customize the layout and focus of applications that show up within Teams |  | On Track |  |  |  | 0%
Configure and enable Frontline Workers with SMS Sign-in |  | On Track |  |  |  | 0%
Manage shift-based access for Frontline Workers in Teams |  | On Track |  |  |  | 0%
Configure messaging experience |  | On Track |  |  |  | 0%
Building block apps enabled, deployed and published |  | On Track |  |  |  | 0%
Ongoing content strategy established |  | On Track |  |  |  | 0%
Define frontline worker / frontline manager roles in Teams (owner vs. member) |  | On Track |  |  |  | 0%
Established Team and channel structure including membership strategy (dynamic, static, naming conventions) |  | On Track |  |  |  | 0%

## people
There are two groups of stakeholders you'll want to assign:
(1)a sponsorship coalition that includes executive and project sponsors who have a vested interest in and influence on the project's success
(2)the project team, consisting of the people responsible for ensuring technical and user readiness, who will complete the various tasks in the project plan.
The common thread between these two groups is the project manager, who works to ensure that project tasks get completed on schedule and reports project status back to the coalition.
Optionally, you can create a steering committee.
Name | Contact details | Role | Part of | Notes
List from people tab table |  |  | Steering committee